Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 11 July 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Customer Registry |
| Maximum Marks |  |

# Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration & Login | USN-1 | As a user, I can register by entering my name, email, password, and role. | 2 | High | Hema Chakravaram |
| Sprint-1 |  | USN-2 | As a user, I can log in and get redirected based on my role (Customer/Agent). | 2 | High | K Hemchand |
| Sprint-1 |  | USN-3 | As a user, I get a clear error if I use a duplicate email or wrong password. | 1 | Medium | Sali Manaswini |
| Sprint-2 | Customer Profile | USN-4 | As a customer, I can create and update my profile details. | 3 | High | Shaik Heeralal |
| Sprint-2 |  | USN-5 | As an agent, I can search and filter customer records. | 2 | Medium | Himabindu Meti |
| Sprint-3 | Complaints / Tickets | USN-6 | As a customer, I can raise a complaint with a subject and description. | 3 | High | Hema Chakravaram |
| Sprint-3 |  | USN-7 | As a customer, I can view the status and history of my complaints. | 2 | High | K Hemchand |
| Sprint-3 |  | USN-8 | As an agent, I can reply to a complaint and it becomes 'In Progress'. | 3 | High | Sali Manaswini |
| Sprint-4 | Agent Dashboard | USN-9 | As an agent, I can view a dashboard with total, pending, and resolved counts. | 3 | Medium | Hema Chakravaram |
| Sprint-4 |  | USN-10 | As an agent, I can mark a complaint as Resolved. | 2 | High | K Hemchand |

# Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date (Planned) | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 5 | 6 Days | 09 Jun 2026 | 14 Jun 2026 | 5 | 14 Jun 2026 |
| Sprint-2 | 5 | 6 Days | 16 Jun 2026 | 21 Jun 2026 | 5 | 21 Jun 2026 |
| Sprint-3 | 8 | 6 Days | 23 Jun 2026 | 28 Jun 2026 | 8 | 28 Jun 2026 |
| Sprint-4 | 5 | 6 Days | 30 Jun 2026 | 05 Jul 2026 | 5 | 05 Jul 2026 |

# Velocity

With a 6-day sprint duration and total story points of 23 across 4 sprints, the team's average velocity was approximately 5.75 story points per sprint, or roughly 0.96 story points per day.

# Burndown Summary

All planned story points were completed on schedule in each of the 4 sprints, with no carry-over work — reflecting steady, on-time delivery from Sprint-1 (setup & auth) through Sprint-4 (agent dashboard & polish).